## Sheet1
|  | Update: | 2026-04-15
| Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
| 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-10
Project Overview Brief | bar: 2026-04-03
Project Specification Paper | bar: 2026-04-10
Test Config variants defined | bar: 2026-04-17
ACK/NACK metrics and protocol defined | bar: 2026-04-17
Functional end-end code | bar: 2026-04-24
Functional Data capture output and logging | bar: 2026-05-01
Debugging and test | bar: 2026-05-01 to 2026-05-08
Paper Drafting - Code documenting | bar: 2026-05-08 to 2026-05-15
Application Demo | bar: 2026-05-08
Test Execution Window | bar: 2026-05-15 to 2026-05-22
Results analysis | bar: 2026-05-15 to 2026-05-22
Paper Drafting - Test bed and Results | bar: 2026-05-22 to 2026-05-29
Project Video | bar: 2026-05-29 to 2026-06-05
Github Repo Submission | bar: 2026-06-10
Legend: | 2026-04-03: Complete
Software Development
Analysis and Paper
Critical Milestones
|  |  |  | Update: | 2026-04-29
| Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
| 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-10
Project Overview Brief | bar: 2026-04-03
Project Specification Paper | bar: 2026-04-10
Test Config variants defined | bar: 2026-04-17
ACK/NACK metrics and protocol defined | bar: 2026-04-17
Functional end-end code | bar: 2026-04-24
Functional Data capture output and logging | 2026-05-01: <---Moved Left
Debugging and test | 2026-05-01: <---Moved Left
Paper Drafting - Code documenting | 2026-05-08: <---extended Left
Application Demo | 2026-05-08: Some Results Available
Test Execution Window | 2026-05-15: <---Moved Left
Results analysis | 2026-05-15: <---extended Left
Paper Drafting - Test bed and Results | 2026-05-22: <---extended Left
Potential Extension | 2026-05-29: Added
Project Video | bar: 2026-05-29 to 2026-06-05
Github Repo Submission | 2026-06-10: <---Moved Left
Legend: | 2026-04-03: Complete
Software Development
Analysis and Paper
Critical Milestones
Plots to compare without wafeform/company info?
refresh project overview
Test bed, equipment, etc
Explain metrics and techniques.
Halow??? Long range WiFi
|  |  |  | Update: | 2026-05-08
| Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
| 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-10
Project Overview Brief | bar: 2026-04-03
Project Specification Paper | bar: 2026-04-10
Test Config variants defined | bar: 2026-04-17
ACK/NACK metrics and protocol defined | bar: 2026-04-17
Functional end-end code | bar: 2026-04-24
Functional Data capture output and logging | bar: 2026-05-01
Debugging and test | bar: 2026-05-01 to 2026-05-08
Paper Drafting - Code documenting | bar: 2026-04-24 to 2026-05-15
Application Demo | 2026-05-08: Some Results Available
Test Execution Window | bar: 2026-05-01; 2026-05-15
Results analysis | bar: 2026-05-01 to 2026-05-22
Paper Drafting - Test bed and Results | bar: 2026-05-08 to 2026-05-22
Final Paper Review and Completion | bar: 2026-05-29 to 2026-06-05
Potential Extension | bar: 2026-05-29 to 2026-06-05
Project Video | bar: 2026-05-29 to 2026-06-05
Github Repo Submission | bar: 2026-06-10
Legend: | 2026-04-03: Complete
Software Development
Analysis and Paper
Critical Milestones